## Slide 1: SD5953 Successful Project Management ASSIGNMENTS, ESTIMATES & COSTS
School of Design
The Polytechnic University of Hong Kong

## Slide 2
IMPORTANT
Please sit with the members
of your final group project

## Slide 3
polyusd5953@gmail.com
Graham Leach, Instructor
www.graham-leach.com

## Slide 4: Assignments = People
The MOST Difficult Aspect of Project Management

## Slide 5: Get a Project Champion
Project Champions are critical to Projects. The best Project Champion comes from the highest levels of organizational power, understands the Project and also knows the strengths and weaknesses of the Project Manager.
The Project Champion usually acts as a mentor. Their role is primarily political, and they are not project “workers”.
Avoid “Project Fatigue”. Use your Project Champion sparingly and only if all other avenues and alternatives are exhausted.

## Slide 6: Dealing With Human Resources
Your Improbable Ally

## Slide 7: The Project Talents Roster
Until now, your Project plan has mostly dealt with the inputs of the Project, not its people. In other words, the talents the Project requires as opposed to its identities.
Identities now need to be established. The first step is to prepare a Project Talents Roster that lists all of the skills the Project needs to complete successfully.
It is at this point where missing or unavailable talents in the Project will appear. This creates a Project “Talent Gap” list.

## Slide 8: Moving From Talents to Identities
In most cases, the Project Charter will have already identified some critical talents (or at least some candidates with those critical talents). Now, actual identities with the needed talent need to start being booked into the Project.
HR is an invaluable resource here. They normally have a good handle on the talent within an organization. If you are lucky, they even have a “Skills Inventory” or can quickly create one.
HR can also be useful in terms of helping you to locate and secure any external or freelance talent needed by the project.

## Slide 9: Getting Talent “Buy In”
Obtaining Talent “Buy In” is a multi-skill task composed of formal, social and organizational skills. The Project Manager must appear “fun” to work with. The Project must have a healthy prognosis. It must look well-organized. Nobody wants to work on a Project that is not:
            Important
            Organized
            Relevant
            Fun

## Slide 10: Obtaining Needed Resources
Based on the authority conferred by the Project Charter, the Project Manager soon begins the process of enlisting the (often scarce) Talents required by the Project.
Formal communications will now flow between the Project Management Office (PMO) and the organization regarding booking of specific talents into the Project at specific times.
At this point, resistance might develop as specific resources are impacted by the needs of the project. This is the first true hurdle for many Project Managers in their Project.

## Slide 11: Resistance
The BANE of Project Management

## Slide 12: Identifying Resistance
There are two varieties of resistance:
  Individual: The implicated Talent feels that they have the personal authority or power to resist becoming involved with the Project. This is the “prima donna” effect.
  Institutional: The implicated Talent feels that their existing authority structure does not support their involvement in the Project and so resists. This is the “good soldier” effect.

## Slide 13: Some Motivations for Resistance
There are a myriad of reasons why people resist becoming involved in projects. Here are some (but not all) reasons:
  Some people are very “loyal” to their existing manager(s)
  The work required by the Project may not be interesting
  Project work is often perceived as “extra, unpaid” work
  Some people are simply lazy and only do the minimum
  The Talent involved may dislike the Project Manager
  The Talent being requested is planning to quit
  The Talent is already feeling over-subscribed

## Slide 14: How to Overcome Resistance
The first step to overcoming resistance is to properly identify the source of the resistance, its intensity and its motivation.
Be careful. There may be multiple agendas at work, each coming from a different point and at a level of intensity. This phenomena is called “the black cloud”.
The easiest way to overcome “the black cloud” is to use the authority of the Project Charter…and involve your “Project Champion” if resistance is ultimately insurmountable.

## Slide 15: Estimating Task Durations

## Slide 16: PERT Analysis
The Program/Project Evaluation and Review Technique, commonly abbreviated PERT, is a statistical tool used in project management. It is designed to simplify the planning and scheduling of large and complex projects.
PERT was first was developed for the U.S. Navy Special Projects Office in 1957 to support the U.S. Navy's Polaris nuclear submarine project.
PERT is commonly used with the Critical Path Method (CPM)
http://en.wikipedia.org/wiki/Program_Evaluation_and_Review_Technique

## Slide 17: PERT Inputs
Optimistic (O): The minimum possible time required to accomplish a task, assuming everything proceeds better than is normally expected.
Pessimistic (P): The maximum possible time required to accomplish a task, assuming everything goes wrong (but excluding major catastrophes).
Most Likely (M): The best estimate of the time required to accomplish a task, assuming everything proceeds as normal.
http://en.wikipedia.org/wiki/Program_Evaluation_and_Review_Technique

## Slide 18: PERT Output
Using the Optimistic, Pessimistic and Most Likely as inputs, the PERT model produces and uses the following output:
Expected Time (TE): the best estimate of the time required to accomplish a task, accounting for the fact that things don't always proceed as normal (the expected time is the average time the task would require if the task were repeated on a number of occasions over an extended period of time).
TE = (O + 4M + P) ÷ 6
http://en.wikipedia.org/wiki/Program_Evaluation_and_Review_Technique

## Slide 19: MS-Project and Task Estimating
MS-Project uses the PERT method to help Project Managers deal with the uncertainty related to estimating task durations.
MS-Project helps Project Managers “triangulate” on task durations by estimating them under different scenarios:
              Optimistic
              Pessimistic
              Best Guess

## Slide 20: Maintaining Talent “Buy In”
Projects are composed of equal parts of:
              Politics
              Socializing
              Work
              Talent
              Skill
Forget this and you will probably have a difficult Project. One easy way to obtain Talent “buy in” is to ask them to help with estimating the durations of their Project-related tasks.

## Slide 21: The Price of Talent

## Slide 22: Costs in MS-Project
Time and Money are the most important costs associated with a Project. MS-Project provides for several types of costs:
Rate Based Cost: Calculated based on the unit rates for a resource multiplied by the amount of units performed.
Per Use cost: Calculated each time the resource is used, or once for each complete task that the resource is assigned to.
Fixed Cost: A fixed cost does not change, regardless of task duration or the work performed on the task by a resource.
http://office.microsoft.com/en-001/project-help/overview-of-project-cost-information-HA001223194.aspx

## Slide 23: YouTube Tutorials
301: Assigning Resources to Tasks
  http://www.youtube.com/watch?v=uHAw5qjF16c
302: Task Types in MS-Project
  http://www.youtube.com/watch?v=-_Gcoqqs3TY
303: Dealing with Work Resources in MS-Project
  http://www.youtube.com/watch?v=cpCpxdB67QI
304: Dealing with Cost Resources MS-Project
  http://www.youtube.com/watch?v=N2-k941wL6Q

## Slide 24: Questions?

## Slide 25: Thank You